Monitoring & Evaluation Form - All Wales Weight Management Pathway Report

| Organisation | CTMUHB |  | Allocation | £439,000 |  | Date of Mid-Year Report | 14 September 2022 |  | Mid-Year Report Prepared By | Head of Nutrition and Dietetics, Principle Public Health Practitioner Project Lead, Life Sciences Hub Wales |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Date of End of Year Report | 14 April 2023 |  | End of Year Report Prepared By | Adult Weight Management Service Professional Lead Principle Public Health Practitioner Deputy Head of Nutrition and Dietetic Professional Manager for Public Health |

The Deputy Minister for Mental Health, Wellbeing and Welsh Language agreed funding of £6.5m to support the delivery of Healthy Weight: Healthy Wales, which included £2.9m to deliver Pathway Transformation Plans. The Children and Families Pathway is one in a series of documents laying out the components, standards and guidance to support the development and delivery of weight management services across Wales. The pathway sets out the key elements and principles underpinning the planning, commissioning and delivery of weight management services for the population of Wales. Reporting Schedule: The Adult and Children’s Weight Management Pathways timetable for funding and reporting is detailed below: - Submission of Draft Plan – 30 April 2022 - Peer Review of Plan – 18 May 2022 - Final Sign Off of Plans – 30 June 2022 - Interim Report – 14 September 2022 - Final Report – 14 April 2023 Progress against the organisation’s plan is to be reported bi-annually. This form is to be submitted on: - 14 September 2022 (covering the period 1 April 2022 to 31 August 2022) - 14 April 2023 (covering the period 1 September 2022 to 31 March 2023) Completed form to be returned to: hss.performance@gov.wales

To be completed by Welsh Government on receipt of Monitoring Form Total allocation; £. Total spend; £. Total agreed; £. Total reimbursement; £.

Update on the actions implemented during the current operational year to advance the development of the AWWMP in the health board’s day to day activities

|  | Key actions planned | Risks to delivery corrective actions & by when including a timeline | What was achieved | Spend actual and planned including a breakdown of resource time | Spend of HB core budget against HWHW | Prevention fund investment into pathway L 1&2 |
| --- | --- | --- | --- | --- | --- | --- |
| Planning |  |  |  |  |  |  |
| 1. Ethos of Healthy Weight: Healthy Wales is embedded into service change/transformational programmes and service delivery plans | 1.1: Ensure that Healthy Weight: Healthy Wales is a core priority in the HB’s CTM2030 strategy for creating health in our population. 1.2: Align CTMUHB weight management service (WMS) pathways with other HWHW initiatives throughout the health board. 1.3: Ensure systems in place for continual development of the service. 1.4 Ensure that Make Every Contact Count (MECC) is adopted throughout the health board 1.5: Ensure sufficient psychological support is embedded into the WMS. | RISK 1.1: There is a risk that without strong governance arrangements the ethos and implementation of the strategy will not be met. ACTION 1.1: Establish governance arrangements for WMS linking into CTM Healthy Weights group and Public Health and Primary Care Oversight Group. TIMELINE 1.1: September 2022 T1.1: Achieved R1.2: There is a risk that patients on other pathways who would benefit from the WMS may be overlooked without alignment of services. A1.2: Aim to have single access point for WMS and members of the implementation board who are involved in other work within health board to ensure alignment. T1.2: December 2022 T1.2 Achieved R1.3: There is a risk that we could miss key opportunities to include novel innovations/transformational programmes into the service that would benefit patients. A1.3: Meet regularly with key R&D, academic and industry partners to discuss the service and research opportunities. T1.3: October 2022. T1.3: Achieved and ongoing R1.4: There is a risk that we won’t be treating patients holistically to maximise patient outcomes at every contact. A1.4: Working closely with local public health team MECC lead to develop training programme for staff. T1.4: On-going. T1.4: Some initial training achieved, wider MECC role out ongoing. R1.5: There is a risk that some patients will require psychological support to support their weight management as obesity is linked to a range of psychological triggers. R1.5ii Lack of capacity in the psychology team will result in delays to psychological intervention and limit the capacity of the sole post holder to develop the service and ensure psychologically informed. A1.5: Recruitment of highly specialist psychologist to inform service development. A1.5ii: Recruitment of a Psychology Assistant T1.5: September 2022. (Achieved) T1.5ii: April 2023 | 1.1: Weight management services are a core priority in the CTM2030 strategy in creating health and improving care (Please see Appendix 1). Strengthening of the WMS governance structure was undertaken to support service implementation, following funding allocation. (Please see Appendix 2). WMS is part of wider “CTM Health Weights” (wider determinants) strategy group. WMS reporting is via the Public Health and Primary Care Oversight Board chaired by the Exec Director of Public Health. Healthy people, healthy settings, developing leadership, enabling change and healthy environment are all keen themes within the CTM 2030 strategy and the HB values and behaviours. 1.1 The Nutrition and Dietetics service including the CTM adult weight management service (AWMS) continues to be a key stakeholder in the CTM Healthy weights group. The Weight Management Implementation Group continue to meet monthly with wider stakeholders. The AWMS continues to report bimonthly into Primary Care and Public Health oversight board. 1.2: Members of the Implementation Board are engaged in work to align the WMS to other work within the HB, such as All Wales Pre-diabetes programme, local pre-diabetes programme, Fatty Liver pathway development, R&D group, diabetes education and WISE (Wellness Improvement Service) for example. The weight management service also reports to CTMUHB’s Value Based Health Care board to ensure alignment and realisation of benefits. 1.2 A single point of access has been created as part of the Level 2/3 Integrated Adult Weight Management Service in CTMUHB. Pathways have been designed in collaboration with stakeholders to ensure alignment with other initiatives 1.3: Included key stakeholders in the continual development of the weight management service via multi-professional steering group and established WMS R&D group. 1.3 Regular steering and implementation groups are ongoing to ensure continuous development. Initial meetings have been held with Key R and D partners and more frequent meetings are being planned. 1.4: Working closely with the LPHT MECC lead to develop a weight specific programme delivered to priority health board staff (primary care, outpatients) as well as wider delivery to local authority staff. This will ensure that non-stigmatising, empathetic behaviour change conversations can take place with all patient groups and residents in CTM. - MECC training has been delivered to colleagues in the Growing Well and Starting Well Strategic Groups with a tailored focus on health weight conversations and included information about weight bias and stigma. In addition, CTM public health team colleagues have contributed to the development of specific Healthy Weight MECC modules which is being led by Public Health Wales. 1.5: A highly specialist psychologist has been recruited to ensure all parts of our pathway are psychologically informed and dignified for service users and patients. In many cases there is a need for specialist psychologically informed support through a skilled team of professionals to support positive lifestyle change. 1.5ii: Whilst funding was for a 1.0 WTE Clinical psychologist, post older only recruited to 0.8 WTE. The remaining 0.2 WTE was used alongside redesign of a support worker post to enable recruitment of a 0.88 WTE psychology assistant to increase psychology capacity. This Assistant Psychology post is in recruitment. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 2. Progress against Level 2 services 2.1 Children and Young People | 2.1.1: Establish Children’s weight management implementation group in line with weight management governance structure. 2.1.2: Establish business case for children’s WMS. | R2.1.1: There is a risk that the Children’s WMS implementation group will not be supported by stakeholders. A2.1.1: Establishing good governance arrangements around Children’s WMS in line with strategic direction. Work with and influence stakeholders to develop a collaborative approach to business case development. T2.1.1: September 2022 T2.1.1: April 2023. R2.1.2: There is a risk that the Children’s WMS business case will not be supported. A2.1.2: Work with stakeholders and executive lead to develop business case based on local needs and identified gaps in service provision. T2.1.2: December 2022. T2.1.2: April 2023 | 2.1.1: Children’s Weight Management Service Governance Structure reviewed and agreed. 2.1.1: Governance structure has been implemented for the CYP workstream, which report into CTM Healthy Weights Steering Group and the Primary Care Public Health Oversight Board. This work is aligned to the CTM 2030 strategy. Q5partners have been commissioned to work with stakeholders and the health board WMS leads to develop an option appraisal for a children, young people and families Level 2/3 WMS. Stakeholders have met regularly to coproduce and inform the business case development and workshops have been conducted. The business case is expected April 2023. 2.1.2: Secured additional senior PHW practitioner resource to support the development of Children’s WMS business case. 2.1.2: 0.4WTE Principal Public Health Practitioner resource in place until end September 2023 to support this work. CYP WMS steering Group established | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 2. Progress against Level 2 services 2.2 Adults | 2.2.1: Undertake process of discovery with health boards across Wales to support the implementation of the CTM WMS. Explore service set up, pathways, group interventions, workforce core competencies and resource required. . 2.2.2: Establish workforce for CTMUHB L2/3 weight management service. 2.2.3: Validate Adult WMS waiting list. 2.2.4 Standardise outcomes within CTM WMS multi-disciplinary team. 2.2.5: Develop single point of access, referral criteria, pathways and design interventions to meet the needs of our population. 2.2.6 Commence level 2 WMS groups (virtual and face to face). 2.2.7: Secure project management support for L2/3 WMS implementation. 2.2.8: Develop communications plan for L2/3 WMS. | R2.2.1: There is a risk that inefficiencies observed by the other health boards during set up could be repeated by CTMUHB. A2.2.1: Collaborative and preventative conversations between health boards to discuss services and lessons learned. A2.2.1 Share progress through forward plans, peer review and professional networks T2.2.1: September 2022 T2.2.1: Ongoing. R2.2.2: There is a risk that the start of the service would be delayed due to issues with staff recruitment. A2.2.2: Improve attractiveness of job descriptions and options for hybrid working offered to incentivise staff. T2.2.2: Please see timelines for recruitment in following box and Appendix 3. R2.2.3i: There is a risk that the number of patients on the waiting list will outweigh the capacity of the new WMS service, as there are currently 894 patients on the WMS waiting list. A2.2.3i: New waiting list validation process established and implemented. T2.2.3i: September 2022. Complete for patients referred up to July 2022 –ongoing now as part of business as usual. R2.2.3ii: There is a risk that the admin processes could cause delays as there is currently limited admin capacity to undertake the validation process. A2.2.3ii: We have advertised additional admin posts and offered additional admin time to therapies admin staff. A2.2.3ii: Admin and clerical are fully staffed since November 2022. T2.2.3ii: September 2022. Complete R2.2.4i: There is a risk that poor reporting of minimum data set will lead to an uncoordinated approach to outcomes and benefits. R2.2.4ii: HB information systems do not fully align with the MDS requirements. The data is inputted in Microsoft Excel manually which is time consuming and increases the risk of human error. A2.2.4: Development of a WMS outcomes framework including process around reporting and alignment into current HB digital systems. T2.2.4: October 2022. T2.2.4: May 2023 R2.2.5: There is a risk that the start of the service will be delayed due to this being a new service and all pathways, referral criteria and patient information needs to be developed and refined through quality improvement process, which will take time. A2.2.5: We have met with other HBs to understand their service configurations, pathways, referral criteria and group interventions. Reviewing this information and establishing the local procedures are the priorities of the newly appointed clinical lead dietitian and psychologist. T2.2.5: November 2022 T2.2.5: April 2023 R2.2.6i: As per risk 2.2.3 and R2.2.6ii: There is a risk that there will be a delay to the L2 service delivery as we will need to develop group content, patient information, pathways etc. prior to the implementation of the service both virtually and face to face. This programme will also need to be tested and validated to meet the L2 offer. A2.2.6ii: Agreement with CAVUHB to utilise their ‘Eating for life’ programme to ensure short timeframe from recruitment to service delivery. T2.2.6ii: August 2022. Achieved A2.2.6iii Develop HB level 2 pathway to include a choice of value based interventions T2.2.6iii achieved and will be reviewed ongoing A2.2.6iii: Complete evaluation of Eating for life service user and staff delivery experience and share learning with CAVUHB. R2.2.7: There is a risk that without coordinated project management support and in the absence of the service manager (due to recruitment difficulties) the implementation of the L2/3 WMS would be piecemeal and will not deliver at the pace that is required for our population. A2.2.7: Project management support secured from Life Sciences Hub Wales for the implementation of the L2/3 adult WMS. T2.2.7: July 2022 Achieved R2.2.8: There is a risk that poor communication of service to health professionals and service users will result in the service not reaching desired target population, or poor referrals with lack or limited information. A2.2.8: Develop communication plan to cover launch of service, how to refer and single point to access. Engage with CTM communications team. T2.2.8: October 2022 T2.2.8: Achieved | 2.2.1: Meetings with other health boards service managers to understand their requirements and lessons learned. Collaborative working and learning from each other. Engagement with CAVUHB, ABUHB, HDUHB and BCUHB to date. Following each meeting the information gathered is shared with our WMS team and discussed at the implementation group. This information is now being used to influence the WMS delivery plan for CTMUHB. Strong working relationships with other WMS have been developed. 2.2.1: Collaborative conversations with other health boards continues. Meetings with Cardiff & Vale UHB and Swansea Bay UHB colleagues were held in March 2023 with a specific focus on the their CYP and Families WMS. The learning from this will inform the development of CYP and Families WMS in CTM. Continue to attend Healthy Weight Healthy Wales Allied Health Professionals Group and appropriate task and finish groups. CTM now represented at Healthy Weight Healthy Wales Allied Health Professionals Group for ongoing professional development, networking and service developments such as commissioning commercial providers 2.2.2: Across the Level 2/3 service we have successfully recruited to: - project support officer - 3x dietitians - 2x dietetic assistants We are actively recruiting to: - Service manager (second time of advertisement, interviews planned for w/c 26th September 2022). - Physiotherapist (interview planned for end of September 2022) - 2x administrators (interview planned for end of September 2022). - 2x dietitians (interviews w/c 26th September 2022). 2.2.2: Recruitment has been challenging with some posts requiring more than one round of advertising due to lack of suitable candidates and some staff have progressed onwards. Across L2/3 Service, the following posts are recruited to: 1 Service Professional Lead 2.6 Dietitians 0.8 Clinical Psychologist 1 Physiotherapist 1 Project Support Officer 2 Admin and Clerical GP with Extended role (sessional basis) 3 Dietetic Assistant Practitioners The following posts are vacant: (all in recruitment) 2WTE Dietitians (of which one is a split post with Diabetes due to funding streams) 0.6 Physiotherapist 0.88 Psychology Assistant 0.2 Consultant 0.2 Specialist Nurse. 2.2.3: New waiting list validation process agreed and commenced. Letters sent to patients to establish if they still require WMS and to identify preferences of service delivery (face to face or virtual). To support patients with the virtual groups we have linked with NHS virtual volunteers who support patients to get online. Also established weekly highlight reports/dashboard on validation process to track numbers of validation letters sent and patient responses. 2.2.3i The validation process of patients referred up to July 2022 is complete (n=795). Of these, 272 responded positively to the offer of a level 2 weight management group or Dietetic 1:1 where group education was not appropriate. All patients referred since 1st July 2022 have been triaged to Level 2 or 3. Current waiting list for Level 2, n=84, Level 3, n=385. 2.2.4: WMS outcome framework being developed to support the reporting of the WG minimum data set and the collection of PROMS and PREMS. This will ensure a coordinated approach across the service and by each professional group. This work is being supported by the HB’s VBHC team. Further work is required to establish digital integration of outcomes framework once this is established. 2.2.4: Draft version of the Minimum Data Set has been used to inform the development of the Excel database to include the data collection points. This has also informed the development of pathways and data collection points in Level 2 and 3. As the service is being set up the AWMS outcomes framework is in progress and will be ratified by the multiprofessional steering group. There is a HB agreed Therapies PREM which is included into pathways. 2.2.5: Networking with other WMS, leading to sharing of information. Understanding of their mistakes in implementation and lessons learned has helped refine our own implementation. Digital options for single point of access are being developed via MS forms. Clinical psychologist post commenced 6th September 2022 and we have negotiated early start for clinical lead dietitian (started 1 day week 26th Aug 2022) who will review the other HB information and develop local procedures. They will also review the emotional regulation offer for L1/L2 services and the CAVUHB “Eating for Life” programme. Met with CTM stakeholders such as primary care directorate, WISE (Wellness Improvement Service), Liver MDT and Staff Wellness Service (WM service) to ensure alignment of services, collaboration and development of integrated pathways. 2.2.5: Agreed criteria for AWMS. See Appendix 6. Pathways have progressed for L2 and L3 and are still in draft format while finalising SOS/PIFU element and the inclusion of a commercial provider. 2.2.6: Collaborative working with CAVUHB WMS to ensure quicker implementation of service, through the use of ‘Eating for Life’ programme. Tailoring of service planned upon recruitment of professional service manager, WM specialists and feedback from patients. Through waiting list validation, patient can choose mode of delivery (face to face or virtual) to meet their needs, including support to help digital inclusion. 2.2.6 Eating for Life has been used with kind permission from CAVUHB to deliver Level 2 groups in person and virtually for patients referred up to July 2022. The last cohort will complete April 2023 and an evaluation of service users and staff delivery will be completed and shared with CAVUHB. The service now offers a range of level 2 options that include FoodWise, Joint Care Programme (JCP), psychological intervention and/or 1:1 dietetic intervention. A commercial offer is also planned at level 2. 2.2.7: Due to recruitment issues with the service manager post we identified the need for senior project management support. With the support of the UHB’s Project Management Office we have secured project management support from Life Sciences Hub Wales (LSHW)to develop an implementation plan and support its implementation. 2.2.7: Following recruitment and appointment to the post of professional service manager, LSHW completed a transitional hand over period of support. Project management now sits with Professional Service Lead. 2.2.8: Working with stakeholders to engage with service design and ensure pathway alignment. Communication plan to be developed in October 2022 and meet with CTM comms team to discuss plans, social media presence and how best to communicate new service information. 2.2.3: Engaged with communications teams and phased communications plan produced. Phase 1: Communication was limited to healthcare professionals by sharing information through the staff intranet and through the Primary care newsletter and through professional networks such as therapy teams. Phase 2 communications are planned with a service user focus to include links to the self-referral route to the service. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 2. Progress against Level 2 services 2.3 Maternity | 2.3.1: Continue to deliver Bump Start service for those with BMI > 40. 2.3.2: Expand upon current service to include those with BMI 35-39.9. | R2.3.1: There is a risk that there will be no dietetic workforce to support the delivery of Bump Start. A2.3.1: Develop business case for dietetic support for Bump Start and to ensure on-going quality assurance of nutritional component of service. T2.3.1: December 2022. T2.3.1: September 2023 R2.3.2: There is a risk that the service will not align with HWHW due to the limitations of the BMI inclusion criteria. A2.3.2: Review BMI inclusion criteria and impact on service demand and capacity. T2.3.2: December 2022. T2.3.2: May 2023 | 2.3.1: This service has been running for 7 years, and is provided by public health midwives. BMI > 40 accounts for 8.2% of the population in CTMUHB and 93% were referred (reasons for non-referral include late miscarriage, late booking. Transfer in late, moving out of area). 83% of referrals engaged with the service, which has risen since last year. The average weight gain during pregnancy was 4.4 kg (gradually decreasing year on year), the low birth rate was 7% (only 1.1% of these were term babies, compared to 1.5% last year). 0.4% still birth rate within this BMI group (however all still births did not engage with the service). Learning shared with All Wales Weight Management Pathway Group. 2.3.1: This service continues, now in its 8th year and the 22/23 outcomes will be evaluated April 2023.There remains a gap for dietetic support which is still being scoped. 2.3.2: First full year of service complete. BMI 35-39.9 accounts for 11% of pregnant population and is provided by community midwives. 89% were referred to the service. Average weight gain during pregnancy was 7 kg, low birth rate was 7.3% (2.6% were full term babies). Further outcomes and acceptability of the service is about to be audited. Quality improvement within maternity supporting development of service. Breastfeeding rates have increased from 46% (20-21) to 50% (21-22). Continue to align maternal weight management support with adult weight management offer and Children and families pilot in Merthyr (PIPYN). Ongoing review and evaluation of the service planned | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 3. Progress around Level 3 services 3.1 Children and Young People | 3.1.1: Establish Children’s weight management implementation group in line with weight management governance structure. 3.1.2: Establish business case for children’s WMS. 3.1.3: Ensure the most vulnerable children with high complexity are offered weight management advice. | As per section 2.1.1 As per section 2.1.1 As per section 2.1.2 As per section 2.1.2 R3.1.3: There is a risk that the number of patients requiring unfunded dietetic services may out-weigh the service capacity. The current dietetic offer to children with highly complex needs is not part of a formal pathway or MDT but is based on individual clinical need. A3.1.3: On-going monitoring of referral numbers into dietetic 1:1 clinics. T3.1.3: On-going. No change | As per section 2.1.1 As per section 2.1.1 As per section 2.1.2 As per section 2.1.2 3.1.3: In the absence of a formal Level 2/3 Children’s weight management service, 1:1 dietetic led services are offered to a small subset of children referred with the most urgent need. Assessment of need is based on individual referrals. Between June and Aug 2022, 50 referrals have been received and either seen by dietetics or signposted to first line advice or HENRY. 3.1.3: Ongoing delivery of dietetic 1:1 for those with urgent need. Ongoing delivery of Henry (70 referrals into Henry Sep – Dec 22) | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 3. Progress around Level 3 services 3.2 Adults | In addition to the progress outlined in level 2 adult service (section 2.2) the following describes specific activity targeted at level 3. 3.2.1: Establish workforce for Level 3 weight management service. 3.2.2: Develop appropriate pathways for the use of weight loss medication 3.2.3: Undertake L3 service location appraisal. | R3.2.1: There is a risk that the start of the service will be delayed due to issues with staff recruitment. A3.2.1: Improve attractiveness of job descriptions and options for hybrid working offered to incentivise staff. Work with medical directorate regarding job planning of consultant lead post and nurse post. Work with primary care directorate for GPwER post. T3.2.1: Please see timelines for recruitment in following box and Appendix 3. R3.2.2: There is a risk that the pathway and number of referrals for Saxenda will be inappropriate as the number of patients eligible to receive weight loss medication Saxenda is unknown in CTM and there is currently no local pathway for its use. A3.2.2: Recruit to secondary care consultant to provide oversight of pathway development. T3.2.2: November 2022 T3.2.2: Ongoing R3.2.3: There is a risk that the location of the service may not be the most appropriate for this patient group. A3.2.3: Early discussions and involvement of Health & Safety team to ensure appropriateness and maintain patient dignity and safety. T3.2.3: July 2022. R3.2.3ii: DSH bariatric space has limited availability- only available on Mondays for the L3 clinic which results in a disproportionate affect from Bank Holidays affecting capacity. A3.2.3ii: Ongoing scoping for suitable alternative accommodation. T3.2.3ii June 2023. | 3.2.1: In addition to the staff described in 2.2.2 Level 2 adult service, we have successfully recruited to the psychology lead (6th Sept 22). We are actively recruiting to: - 0.2 WTE Secondary care consultant lead – Adding 0.2 WTE to existing job plans is proving difficult therefore in decision with medical directorate they are advertising a 0.6 WTE diabetes role which will allow job planning of Diabetes and Endocrine consultant to support WMS lead post. Currently out to advert (closing on 29th Sept 22). - GPwER – Working with primary care directorate to develop the expression of interest and GPwER scope and job roles prior to advertising. - 0.2 WTE Band 7 nurse, discussions are ongoing with medical directorate around this role and how best to utilise. We are exploring the option of combining this within an existing diabetes nurse post. - Physiotherapist role. Currently exploring internal expressions of interest to scope physiotherapy service needs. Interviews planned for end of September 2022. 3.2.1: Recruitment across Adult L2/3 is outlined in 2.2.2. 3.2.2: Engaged with medical directorate, executive director of public health to expedite job planning and recruitment to secondary care consultant. Engaged with other health boards, pharmacy and Novonordisk around Saxenda pathway. Currently exploring option of GPwER prescribing (learning from ABUHB experience) if unable to recruit to secondary care consultant. 3.2.2: Developed draft pathway for Saxenda in conjunction with the GPwER. Ongoing recruitment conversations regarding consultant post. 3.2.3: Location confirmed for Level 3 MDT service. Newly refurbished bariatric space in Dewi Sant Hospital & designated time in new outpatients clinic space in St Marks building on RGH site. Met with Health and Safety team regarding clinic space. All equipment purchases are supported by health and safety team to ensure patient dignity and safety. 3.2.3: L3 service delivered on Mondays from DSH, clinic space available at Dewi Sant but no suitable clinic space available as yet in Bridgend area. Patient care has been delivered in a virtual setting using Attend Anywhere, face to face clinics, virtual groups on Microsoft teams and face to face groups in Pontypridd and Bridgend. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 4. Comments/updates on Level 1 and Level 4 4.1 Children & Young People Level 1 Weight Management Service Update | 4.1.1: Continue planning and development of Children and Families Pilot Merthyr (PIPYN) and its referral pathway and criteria. 4.1.2: Delivery of a range of evidence based services through Public Health Dietetics / Nutrition Skills for Life: - 2x Community Food and Nutrition Skills for the Early Years - 2x Community Food and Nutrition Skills for schools - Healthy Snack Award 4.1.3: Increase knowledge, referrals and uptake of HENRY. | R4.1.1: There is a risk that the service will outweigh the capacity of the dietetic and school staff. A4.1.1: Additional funding approved by WLGA to pilot dietetic coordination in Merthyr. T4.1.1: from September 2022. Achieved 650% increase in eligible schools sign up in Merthyr in 7 months R4.1.2: There is a risk that there will be insufficient staff as recruitment to key roles has been problematic. A4.1.2: Local public health team resource has been utilised to support programme implementation. T4.1.2: from September 2022. Achieved R4.1.3: There is a risk of low level engagement with the programme from both referrers and families. A4.1.3: In-house awareness sessions developed to be delivered to health and wider key stakeholders. Additional sessions added to the service offering (virtual, face to face, 1:1 and evening sessions) to increase uptake for working families. T4.1.3: On-going. | 4.1.1: Steering group met and TOR developed. Recruitment of family support workers and administrative staff. Family engagement questionnaires produced. 4.1.1 Dietetics and Public Health led Children and Families Healthy Weights Steering Group Coproduction events undertaken and Launch Date planned April 23 – 24 self-referrals received from families prior to launch date 4.1.2: Delivery of a range of evidence based services through Public Health Dietetics / Nutrition Skills for Life and Community Food and Nutrition Skills for Schools. Continued to try to recruit and to be flexible within the roles. Utilise underspend to recruit ex-head teacher to support planning of the programme. Delivery in line with current plan as well as additional Community Food and Nutrition Skills 35 school and nursey staff trained in a settings based approach to healthy weights. Recruitment is an ongoing challenge due to short term nature. Fixed term vacancies has led to increased staff turnover. 2.4 WTE dietetic vacancies now recruited to Public health resource agreed and supporting programme. An active social media account Merthyr PIPYN (facebook.com) website development Pipyn - Cwm Taf Morgannwg University Health Board (nhs.wales) 133 family engagement surveys and 2 focus groups completed to inform service development and support family engagement and informed service procurement/incentives 4.1.3: Between September 2021 and June 2022, 5 cohorts of ‘HENRY – Raise, Engage, Refer’ have been delivered to 51 partners from health and social care professions. Each consists of two online sessions. LPHT HENRY Awareness programme created – 36 professionals currently on waiting list for this. This training will now be delivered on-going to health and social care staff. New Standard Operating Procedures developed for HENRY Waiting Lists to manage referrals and parent contact. Webpage and SharePoint page being created for HENRY. Social media post on Healthy Start Healthy Future reaching over 10,000 views/interactions. KPI agreed for all referred families to be contacted to discuss HENRY programme. Please see Appendix 4 for parent survey overview. 4.1.3: Between September - December 2022, the HENRY programme has received 70 referrals. | Please see Welsh Government quarterly return for Children’s and Families. |  |  |
| 4. Comments/updates on Level 1 and Level 4 4.2 Adults Level 1 Weight Management Service Update | 4.2.1: Delivery of a range of evidence based services through Public Health Dietetics / Nutrition Skills for Life 4.2.2: Roll out of All Wales Diabetes Prevention programme and local CTMUHB pre-diabetes brief interventions. Ensure pathways into WMS. 4.2.3: Re-establish the Joint Care Programme (JCP) to pre-pandemic levels of referral and uptake. 4.2.4: Develop level 1 local content to feed into NHS Healthy Weight website 4.2.5 Align the new CTMUHB staff “Healthy Lifestyle” course to the HB weight management service. 4.2.6: Align adult WMS pathways with Wellness Improvement Service (WISE). | R4.2.1: There is a risk that the cost of venues in communities may be too high for the budget and recruitment and retention of dietetic staff. A4.2.1: Key relationship building with stakeholders in leisure facilities to enhance partnership engagement. Wider advertisement of dietetic workforce in light of national workforce shortages. T4.2.1: December 2022 achieved and ongoing R4.2.2: There is a risk of delays to the programme due to short term funding, general recruitment delays as well as recruitment and retention of registered dietetic staff. A4.2.2: Restructure of public health dietetics team and wider advertisement of dietetic workforce in light of national workforce shortages. T4.2.2: Sept 22 Achieved R4.2.3: There is a risk of low patient engagement due to lack of referrals from other HCP’s into Level 1 services. A4.2.3: Wider communications plan being developed alongside self-referral option. A4.2.3ii: JCP management will move to Nutrition and Dietetic Service from public health to ensure integrated WMS. T4.2.3: September 2022. Ongoing A4.2.3ii: April 2023 R4.2.4: CTM local content will not be available on an All Wales NHS platform. A4.2.4: Develop local level 1 content. T4.2.4: Sept 22. Achieved R4.2.5: There is a risk the new staff healthy lifestyle course will not be aligned to the HB WMS offer, the HWHW pathway and therefore not benefit from the expertise and pathways of the service. A4.2.5: Engage staff wellbeing services and align pathways and service criteria with HWHW. Establish if offer is L1 or L2. T4.2.5: October 2022 Achieved: The offer is L1. R4.2.6: There is a risk that WM pathways will not align between WISE and the new WMS. A4.2.6: Ensure WISE are represented within the implementation group. Collaborate with WISE and Primary Care services to align pathways and service criteria with HWHW. Establish if offer is L1 or L2 and need for triage. Explore option for WMS waiting list. T4.2.6: Oct 2022 Achieved | R4.2.1: Launch of level 1 website content and electronic self- referral system for self-booking. Dietetic triage of patients implemented Delivery of a range of evidenced based services through Public Health Dietetics /Nutrition Skills for Life: - 2x Level 2 Community Food and Nutrition Skills - 10x Foodwise (72 patients) - 10x Get cooking (starting Sept 22) Marketing & Comms plan developed to enhance community and partnership engagement Regional level 1 Foodwise facebook pages developed Dietetics Cwmtafmorgannwg ¦ Facebook All registered dietetic vacancies filled (3.0 WTE Dietetic Assistant Practitioner vacancies) Ongoing delivery of FoodWise and Get Cooking 4.2.2: Restructuring and recruitment of dietetic staff on a permanent basis. Engaged local clusters, implementation groups established. Learning from AWDPP and local CTM pre-DM work. Monthly CPD and supervision provided by dietetic staff with direct referral into Foodwise. 4.2.2: Ongoing collaboration with local pre-diabetes programmes. Referrals from AWDPP are triaged according to level (1-3) required and offered appropriate input/added to corresponding waiting lists. 32% onward referral to WM services 36% onward referral to physical activity 4.2.3: Launch of level 1 website content and electronic self- referral system for self-booking. JCP also accepts referrals from primary and secondary care. Dietetic triage of patients implemented Equipment purchased to support roll out and community engagement work Roll out of JCP pan CTMUHB. BMI referral criteria reduced to ≥25kg/m2 - September 22 to align AWWMP. 4.2.3: JCP has been incorporated as part of the L2 offer in the new service pathway. This is expected to optimise referral rate and uptake. JCP has been promoted on the UHB intranet. Recognising the importance of multimedia content, a service user friendly video walkthrough of the JCP programme has been commissioned and is expected to be ready for publicising April 2023. 4.2.4: Local content fed into central public health team. 4.2.5: 10 week Healthy Lifestyle course developed by CTMUHB wellbeing service with support from public health dietetics. 4 courses completed since Jan 2022. Staff Wellbeing lead is stakeholder on WMS implementation group. Further work required to align pathways for each service, but good collaboration between services has been demonstrated. Please see Appendix 5 for overview. 4.2.6: The Wellness Improvement Service (WISE), developed by the Primary Care team of CTMUHB, will be offering patients from the pre-diabetes and cardiovascular risk programmes opportunities to utilise Second Nature as an additional weight management programme for patients. Primary Care are represented on the Implementation Group to ensure dovetailing of services and appropriate referral for patients. Initial meeting between WMS and WISE has taken place and pathway is being developed. A4.2.6: WISE is a L1 offer and the service can support AWMS patients across the pathway for holistic care including social prescribing, sleep hygiene and emotional wellbeing. Patients awaiting L3 will be signposted to self-refer to WISE while they wait for support with any of the above. |  |  |  |
| 4. Comments/updates on Level 1 and Level 4 4.3 Level 4 | 4.3.1 No Level 4 service available as this is a WHSCC commissioned service provided by Swansea Bay UHB. 4.3.1: Agreement has been made between the AWMS and WIMOS that The Level 3 MDT will be able to refer suitable patients to the level 4 service hosted by Swansea Bay UHB. | N/A | N/A | N/A | N/A | N/A |

|  | Key actions planned | Risks to delivery corrective actions & by when including a timeline | What was achieved | Spend actual and planned including a breakdown of resource time | Spend of HB core budget against HWHW | Prevention fund investment into pathway L 1&2 |
| --- | --- | --- | --- | --- | --- | --- |
| Standards |  |  |  |  |  |  |
| 5. Each Health Board publishes a strategic weight management pathway development plan, agreed with Welsh Government. The plan should set out: an assessment of need to inform priorities for action; a phased development plan; a description of services at each level of the All Wales Weight Management Pathway for adults, children and those with specific needs e.g. pregnant women. | 5.1: Submit the strategic weight management pathway development plan to WG. | R5.1: Funding is the main risk to the expansion of the weight management service to include children and young people. Currently the fixed term WG funding and recurrent HB funding has been prioritised towards the development of an adult integrated service. Prior to 2022 there was no historic investment for WMS in CTMUHB. A5.1: Business case development for Children and Young People’s WMS. Additional resource from LPHT secured to support the development of the business case. T5.1:Dec 2022 See 2.1.1 T5.1: April 2023 | 5.1: Many aspects of the pathway development plan have progressed in the recent months including: - Establishing recurrent HB funding - Agreeing hosting of service within dietetics - Establishing the governance structure and internal reporting for the service - Securing external project management support from Life Sciences Hub Wales for development of L2/3 adult WMS implementation plan. - Several key roles have been recruited into as described above and on-going recruitment continues at pace. - Received recognition from steering group to deliver on the implementation plan. - Validation process of WMS waiting list established and ongoing. - Support provided for digital inclusion to support hybrid offer - Commenced Level 2 adult groups. - Base for service agreed as Keir Hardie Health Park and staff moved into office space. - Working with stakeholders and networks to learn from others, to establish lessons learned and implement at pace. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 6. Health Boards can demonstrate how services in the strategic weight management pathway development plan will meet the needs of the population and reduce inequalities in outcomes. Health Boards should be able to demonstrate that services are: accessible; targeted to specific needs where appropriate and; that monitoring of service uptake considers equity of access for vulnerable groups. Health Boards should report annually on service capacity at each level of the pathway. | 6.1: Develop business case for Children and young people weight management service to be considered by the health board. 6.2: Develop multi-stakeholder steering group to support delivery of the development plan 6.3: Hybrid adult service offer to support efficiencies in service delivery and patient choice. 6.4: Service to be delivered as close to the persons home as possible 6.5: Planned activity around seldom heard groups to increase service engagement | R6.1: There is a risk that the business case development will be delayed due to limited resource and availability of staff. A6.1: Secure LPHT resource, recruit to service manager post, galvanise support for Children’s WMS with clinicians and stakeholders. T6.1: December 2022 ongoing R6.2: There is a risk that there is disconnect between the strategic direction of the organisation (CTM2030), HWHW, the delivery of the WMS and other services. A6.2: Engagement from wider stakeholders and development of WMS steering group. T6.2: Sept 22 Achieved/ongoing R6.3: There is a risk that the lack of patients’ digital skills may prevent them taking up the option of virtual appointments / programmes. A6.3: Engaged with NHS digital volunteers to support digital inclusion prior to appointments. T6.3: Sept 2022 and ongoing. R6.4: There is a risk that there will be a lack of suitable accommodation in community venues. A6.4: Scope local venues. Currently central location within HB with good public transport links, with aims to identify additional locations throughout HB to accommodate those living further afield T6.4: October 2022 Ongoing R6.5: There is a risk that seldom heard groups will not have equitable access to service provision. A6.5: Data collection on demographics essential to describing population. T6.5: Ongoing Ongoing | 6.1: Established new governance structure including a Children and young person’s implementation group, which will provide focus on this aspect of the service. 6.1: See 2.1.2 6.2: Steering group established with deputy director of public health as chair. Wide ranging multi stakeholder representation. Further work required on engagement of external stakeholders and patient feedback and co-production events. 6.2: The AWMS has engaged with a wider Therapies Long Term Conditions Project, which has included extended stakeholder meetings and coproduction events. 6.3: Digital inclusion questions added to validation letters. Offer of additional support to get online provided. Engaged with NHS digital volunteers to support patients prior to appointments / groups. 6.3:A hybrid service is offered across levels 1-3. Feedback from the validation indicated that of the 272 that did require input, 94 preferred face to face groups, 40 preferred virtual and 104 would attend either*. This complements the qualitative research in Appendix 7 that a hybrid offer is appropriate. *34 of the respondents were not suitable for group education and they were offered Dietetic 1:1. 6.4: Scoping of suitable community venues for L2 adult service is currently underway. In addition a list of commonly used venues and contact details has been developed. Working with therapies services to establish wider accommodation need for community venues, work with leisure partners on availability of venues. Level 3 service will be based in Dewi Sant hospital where the lymphedema service is co-located, environment is bariatric friendly and has been reviewed by health and safety. 6.4: Ongoing scoping of suitable venues and collaboration with stakeholders such as WISE, Diabetes education to share detail of suitable venues. 6.5: Referral population data reports need to be developed and evaluated. Monitoring of service uptake and will consider equity of access for vulnerable groups. Collaborative working with HBs VBHC team to identify any under-represented groups. We have developed a piece of qualitative research with Promo-Cymru to understand the enablers and barriers to attendance for patients who are overweight / obese and are also pre-diabetic. A series of interviews and workshops will take place to inform service delivery across pre-diabetes and weight management community deliver. 6.5: Promo Cymru Qualitative research linked as Appendix 7. This feedback was incorporated in development of the L2/L3 pathways. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 7. People with higher body weights are treated with dignity and respect and do not feel stigmatised due to a lack of appropriate equipment or facilities. This includes patient transport and emergency services. | 7.1: Review outpatient locations and equipment available to ensure dignity and respect is maintained. | R7.1: There is a risk that patients will not be treated with dignity and respect due to the setup of outpatient clinics. A7.1: Review outpatient locations and equipment with regards to dignity and respect and ensure HB values and behaviours are maintained. T7.1: Sept 22 Achieved/ongoing accommodation review | 7.1: Planned location of Level 3 service (Dewi Sant) has bariatric friendly equipment and facilities. Worked with Health & Safety department early in planning process. H&S training planned for staff regarding adverse events with bariatric patients. Bariatric weighing scales being purchased for clinic areas. L3 service in Dewi sant will be for those who have a degree of independency when it comes to transport, however online/home visits are being discussed for those unable to get to the service in person. The HB values and behaviours of treating everyone with respect will be embedded within the team as well as opportunities for training and education including MECC. 7.1: BP cuffs utilised in JCP were not suitable for severely obese, and those patients were asked to have their BP taken at their GP surgery, which is a potential barrier for engaging with the service. New BP machines compatible with larger cuffs have been procured for the four JCP sites of delivery. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 8. Planning, commissioning, evaluation and delivery of services actively engages with and involves people living with overweight and obesity. | 8.1: Develop robust evaluation process for the L2/3 adult WMS. 8.2: Develop a process for patient experience and patient stories including the co-production of services. | R8.1: There is a risk that there will be a lack of patient engagement in PROMs and PREMS. A8.1: Develop and implement an outcomes framework including PROMS and PREMS to support ongoing service improvements through patient outcomes and feedback. Good patient understanding of the need for PROMS/ PREMS and patient feedback. Simple easy process that’s not too onerous should be developed. T8.1: Outcomes framework to be developed by Oct 22. T8.1: In progress expected May 2023 R8.2: There is a risk that a lack of patient co-design, co-production and feedback will result in the adult L2/3 services not meeting the needs of the population and the desired health outcomes. A8.2: Develop a process of co-production, patient stories and patient feedback. T8.2: Dec 22 T8.2: Ongoing | 8.1: Engagement with VBHC service to support PROMS/PREMS. Following recruitment to key posts the outcomes framework is a key priority for development. Further work will be required in this area once outcomes framework has been agreed by the service. 8.1 See 2.2.4 8.2: Further work in this area is required. Need to engage with CTM’s Head of public engagement and involvement to ensure the adult WMS used patient experience data and patient stories to improve quality of service delivery. Current work underway as described in 6.5 with Promo Cymru. 8.2: Promo Cymru qualitative research report is linked below as Appendix 7. As mentioned in 6.2, coproduction events are utilised as part of the Long Term Conditions Work to inform the service development. Ongoing development of PROMS and PREMS. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 9. The Weight Management Pathway in the local area is managed and co-ordinated. Services delivering elements of the pathway have a clear understanding of roles and responsibilities and mechanisms to facilitate movement of individuals within the pathway in a seamless manner as needs change. | 9.1: Establish a single point of access for adult weight management services. | R9.1: There is a risk of duplication or omission of service offerings due to multi-disciplinary team approach to weight management service. A9.1: Single point of access to weight management service being developed. Professional service manager is being recruited to oversee the service and assist with collaboration between departments. T9.1: November 2022. T9.1: Achieved | 9.1: Active recruitment for professional service manager on-going (with difficulties previously described in sections 2.2.2 and 3.2.1). Established multi-stakeholder implementation group that meet on a monthly basis. Through the steering and implementation groups, clear roles and responsibilities have been developed, agreed and documented in the Terms of Reference. Collaboration with improvement team to develop single point of access into pathway. 9.1: Professional service manager recruited and single point of access into pathway developed. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 10. Protocols informed by the All Wales Child Protection Procedures (2008) are followed when childhood obesity is a cause for professional concern, regarding wellbeing and risk of harm | 10.1: Embed the All Wales Child Protection Procedures (2008) across the service. | R10.1: There is a risk that children within the services will be at a risk of harm. A10.1: Ensure safeguarding processes are in place and work in partnership with safeguarding leads when developing new service. Safeguarding is part of all staffs mandatory training. T10.1 Ongoing T10.1: Ongoing | 10.1: Establish Children and young person’s implementation group. All staff undertake mandatory child protection training once recruited. Supervision and training opportunities will be available for all staff members. 10.1: All staff undertake mandatory child protection training. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 11. Staff working within the Health Board receive training to enable them to offer compassionate, psychologically informed care that avoids stigma and discrimination. All staff are able to engage in supportive conversations with patients regarding weight management in line with Level 1 of the pathway. | 11.1: Develop training and education to ensure compassionate, psychologically informed care is core to service delivery. | R11.1: There is a risk that a lack of training opportunities for staff could result in sub-optimal care, resulting in poorer outcomes for our population. A11.1: Embed Health Board values across the service. Review training needs of staff with psychologist (started 6/9/22). Review capacity of training provision. Ensure staff undertake MECC training as part of induction. Develop core psychologically informed competencies into service. Ongoing supervision and training updates will be required. T11.1: Dec 202 T11.1: Ongoing | 11.1: This area requires further work as the workforce is currently coming into post. Work is ongoing to establish suitable training around healthy weight and core competencies for the workforce. 11.1: All WM service staff have their training needs reviewed as part of their induction and Personal Development Review (PDR) process. Clinical staff are attending Bridges training to develop skills and confidence in when having supportive conversations for self-management. Bridges Self Management Staff are supported to access MECC training | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 12. The Health Board adopts a continuous improvement approach to service quality and outcomes using the minimum dataset and other mechanisms including patient stories. The Health Board submits returns to Welsh Government in line with the minimum services standards and actively encourages participation in national audit and review. | 12.1: Establish and embed the outcomes framework (includes minimum dataset, PROMS & PREMS) and develop a performance dashboard to enable continuous service improvement, service feedback and reporting to WG. 12.2: Develop a culture of R&D across the weight management service. | R12.1i: There is a risk that there will not be enough capacity of the CTM digital team to support the development of the performance dashboard. A12.1i: Early engagement with CTM digital team. T12.1.1i: Oct 2022 Initial scoping complete but to revisit. R12.1ii: There is a risk that staff will not be able to identify areas for improvement and have the skills and knowledge to implement change. A12.1ii: Engage with iCTM (HB QI department) on training and support for service. T12.1ii: Sept 2022 - ongoing R12.2: There is a risk that without an ethos of R&D, patients will not have access to the most evidence based treatments resulting in poorer outcomes. A12.2: Engage with R&D colleagues and academic partners to establish WMS research group. T12.2: Oct 2022 T12.2: June 23 | 12.1: Outcomes framework in development by clinical lead dietitian and psychologist. Engaged with local VBHC team. Following recruitment of the wider team we will work on incorporating minimum data set into outcomes framework (PROMS & PREMS). Further work is required to engage with digital leads regarding integration of outcomes. 12.1 Initial scoping undertaken with CTM ICT team. There is a lack of HB resource to support performance dashboard. Work ongoing on outcomes framework. Met with iCTM who have agreed training for WMS workforce once recruited. Staff will be supported to undertake service evaluations and QI projects. A12ii Staff from the weight management service are represented at a newly formed ‘Innovation and Improvement Forum within Nutrition and Dietetics where QI activities will be supported. 12.2: Met with R&D department and academic partners to establish WMS Research group. Terms of Reference are being established and first formal meeting due in Oct 2022. Also recruited staff with research experience to help embed this culture across the service. Training and education opportunities will be mapped for the service once workforce is recruited to. T12.2 Due to delays with recruitment and focus on service start the R and D group has yet to start. Plans to commence in Q2 | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |
| 13: Weight management services share their learning with colleagues within and beyond weight management services. | 13.1: Participate in national weight management meeting and contribute to the wider WM agenda both within CTM and nationally. | R13.1.1: There is a risk that by not participating in the national network or sharing learning internally, the CTM WMS will not; be up to date on strategic direction, be able to influence policy and guidance and will not benefit from the wider experts in the WM field. This will result in poorer outcomes for our population. A13.1.1: Engage in national WM network. Engage with local networks and groups to demonstrate the impact of the WMS. T13.1.1: Ongoing T13.1.1: Ongoing | 13.1: Actively engaged in national peer review and all Wales meetings. Outside of these meetings we have undertaken shared learning opportunities with HB across Wales (see section 2.2.1). Governance and reporting agreed, which has a wide range of stakeholders. Aligned reporting of WMS to the HB’s Public Health and Primary Care Oversight Board. This allows oversight by the Exec director of PH and Primary Care Director and alignment to other initiatives across the HB such as diabetes prevention (both the local diabetes prevention programme and the AWDPP), WISE and staff wellbeing programme. Invited to participate in the L3 specialist interest group supported by Novonordisk. PH Dietetic lead is the chair of the All Wales Public Health Dietitians Group. Staff and operational managers engaged in national developments around DM prevention and obesity. The CTM WM services plans to share our learning and actively engage in the network across Wales. Engaged with stakeholders around the development of an integrated WM pathway and establish CPD sessions on weight management. On-going collaboration between health boards WMS service leads and Life Sciences Hub Wales. 13.1.1: Above continues, in addition CTM are now represented at Health weight, Healthy Wales AHP group and contribute to task and finish groups such as “Commissioning commercial providers on a national scale” and “Level 4 Bariatric Services Task and Finish Group”. | Please see Appendix 3. | Please see Appendix 3. | Please see Appendix 3. |

Relevant Strategies and Guidance

AWWMP Guidance https://gov.wales/adult-weight-management-pathway-2021

https://gov.wales/weight-management-pathway-2021-children-young-people-and-families

Weight Management Standards https://gov.wales/weight-management-services-standards

Welsh Government Healthy Weight: Healthy Wales Strategy https://gov.wales/healthy-weight-strategy-healthy-weight-healthy-wales

Delivery Plans https://gov.wales/healthy-weight-healthy-wales-delivery-plan-2020-2022

Welsh Government ‘A Healthier Wales’ https://gov.wales/healthier-wales-long-term-plan-health-and-social-care

Appendix

Appendix 1: CTMUHB Unified Transformation Portfolio

Appendix 2: CTMUHB WMS Governance Structure

Appendix 3: CTMUHB WMS Finance Information March 2023

Appendix 4: HENRY Parent Survey Overview

Appendix 5: Staff Wellbeing Healthy Lifestyle Overview

Appendix 6: Adult Weight Management Service Referral Criteria

Appendix 7: Promo Cymru Research