POPULATION HEALTH & PARTNERSHIPS COMMITTEE ACTION LOG (as at 20.10.22)

| Minute Ref: | MEETING DATE | SUBJECT | KEY ACTIONS/DECISIONS | RESPONSIBLE OFFICER | COMPLETED/ updated |  |
| --- | --- | --- | --- | --- | --- | --- |
| 07/22/08 | July 2022 | Healthy Weights Across CTMUHB | Circulate the research on obesity in the CTM area outside of the meeting. | Philip Daniels | Complete Information provided via email to Members 26.10.22 |  |
| 05/22/05 | July 2022 | Organisational Risk Register | Emerging risk around the capacity to deliver the vaccination programme would be reviewed outside of the meeting via the Strategic Leadership Group and the Committee would be updated at the next meeting for assurance. | Assistant Director of Governance & Risk | Complete Discussions held and no risk has yet to be escalated to the Organisational Risk Register on this activity. |  |
| 05/22/09 | May 2022 | CTM an Anchor Organisation | The Committee agreed that this should be embedded and aligned to the CTM 2030 Strategy. | Kelechi Nnoaham | In Progress Committee advised at July 2022 meeting that the two actions were being worked through and an update would be prepared for the next meeting. |  |
| 05/22/09 | May 2022 | CTM as an Anchor Organisation | The Committee noted the potential for the Anchor programme to have resource implications for the Health Board and agreed to receive a further update. | Kelechi Nnoaham |  |  |
| 10/21/08 | October 21 | Vaccination and Immunisation Update | To receive a further update on the development of the business case developed to deliver a sustainable vaccination and immunisation programme across CTMUHB and progress in relation to the workforce capacity issues | Kelechi Nnoaham | Ongoing Update provided at July 2022 meeting. Welsh Government guidance regarding future vaccination programmes not yet received – update to next meeting. |  |
| 10/21/08 | October 21 | Vaccination and Immunisation Update | Discussions to be held on the challenges with workforce capacity with the Director for People. | Kelechi Nnoaham | Ongoing Update to be provided to next meeting. |  |
| PCCC/20/09 4/21/8 | October 2020 April 2021 | All-Wales Interim District Nursing Compliance and Principles | Informal feedback had been received from Welsh Government which had been positive and a report would be brought to the next meeting. In light of Covid, WG advised not to progress with the next audit, so no formal update available to the committee. July 22 - Update required as to whether this work to resume and if so a date was required. | Greg Dix | In Progress Draft National Community Nursing Specification out for comment – to be circulated once finalised. |

COMPLETED ACTIONS

| 05/22/14 | May 2022 | Partnerships Update |  | Population Needs Assessment and Wellbeing Assessment, once published to be received by the Committee. |  | Linda Prosser/Kelechi Nnoaham |  | Completed Referenced as part of the Public Service Board Update at the July 2022 meeting. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10/21/6 05/22/4 | October 2021 May 2022 | Healthy Weights Action Log |  | Third Party and Voluntary Sector representatives to be added to the membership of the steering group. Outstanding Action on Healthy Weights to be reviewed outside of the meeting. |  | Kelechi Nnoaham |  | Completed Update Report received at the July 2022 meeting |  |
| 10/21/7 | October 21 | Housing & Homelessness Update |  | Members of the Committee to be invited to attend the Health & Housing summit. |  | Linda Prosser |  | Completed Summit held in October 2022 with invites extended to Members of the Committee. |  |
| 10/21/6 | October 21 | Healthy Weights |  | Discussions to be held with the RPB on engagement and involvement |  | Clare Williams |  | Completed The service has been funded and implementation planning underway. |  |
| 10/21/11 | October 21 | Clinical Analysis Backlog from the Primary Care Information Portal |  | Update on accelerated cluster development to be added to forward work programme |  | Julie Denley |  | Completed Received by the Committee at the May 2022 meeting. |  |
| 2/20/013 | 10.2.20 | Inverse Care Law |  | Agreed to receive further analysis at the next meeting. |  | Kelechi Nnoaham |  | Completed On Agenda July 2022 meeting. |  |
| 7/21/9 | 07.07.2021 | Learning & Disability Strategic Update |  | Data to be provided on numbers of people with learning disabilities receiving health checks, vaccinations and cancer screening in the last year |  | Julie Denley |  | Completed Received by the Committee – May 2022 |  |
| 7/21/12 | 07.07.2021 | Regional Partnership Board Transformation Fund Update | Receive regular updates on how the data from the population segmentation and risk stratification would be used and reflected on the Risk Register |  | Linda Prosser/ Georgina Galletly |  | Completed Risk Register on Agenda – October 2021 – new Risk on the Transformation Fund added to the Risk Register. |  |
| 7/21/11 | 07.07.2021 | Key Findings from HMP Parc Health & social Needs Assessment | Further consideration required from the Executive Team on the process of how the risk would be managed to ensure the Board had oversight due to the complexities and issues that might arise. |  | Georgina Galletly/ Julie Denley |  | Completed Report received by the Committee at the May 2022 meeting. Operational transition will be reported to Management Board and where any risks identified at a level requiring board oversight they will be allocated to the appropriate committee and included on the organisational risk register reported to Board. |  |